## Sheet1
System | Activity | Start | Finish | Deliverable | PIC
E-learning | Analysis current condition | 2017-06-05 | 2017-06-09 | Flowchart Business Process | Martin
| Requirement Gathering | 2017-06-12 | 2017-06-16 | System Requirment Specification | Martin
| Design | 2017-06-19 | 2017-07-02 | System Design Document | Luthfi
| Coding | 2017-07-03 | 2017-07-22 | Source Code | Rohmat
| Testing & Debuging | 2017-07-24 | 2017-07-30 | UAT, Testing Document | Rohmat
| Deploy & Documentation | 2017-07-31 | 2017-08-01 | User Manual, Installation Manual | Faisal
E-recruitment | Requirement Gathering | 2017-07-03 | 2017-07-07 | Flowchart Business Process | Luthfi
| Design | 2017-07-10 | 2017-07-21 | System Design Document | Luthfi
| Coding | 2017-07-24 | 2017-08-11 | Source Code | Rohmat
| Testing, Debuging, Deploy & Documentation | 2017-08-14 | 2017-08-18 | UAT, Testing Document | Rohmat